Council Plan 2021-25 
quarterly report card

January to March 2022

Contents

Economy of the Future	3

Highlights for quarter three (January to March 2022)	3

Our progress	3

The major initiatives we’re delivering this year	3

How we’re measuring progress over four years	4

Melbourne’s unique identity and place	6

Highlights for quarter three (January to March 2022)	6

Our progress	6

The major initiatives we’re delivering this year	7

How we’re measuring progress over four years	8

Aboriginal Melbourne	9

Highlights for quarter three (January to March 2022)	9

Our progress	9

The major initiatives we’re delivering this year	9

How we’re measuring progress over four years	10

Climate and biodiversity emergency	11

Highlights for quarter three (January to March 2022)	11

Our progress	11

The major initiatives we’re delivering this year	11

How we’re measuring progress over four years	12

Access and affordability	14

Highlights for quarter three (January to March 2022)	14

Our progress	14

The major initiatives we’re delivering this year	14

How we’re measuring progress over four years	15

Safety and wellbeing	16

Highlights for quarter three (January to March 2022)	16

Our progress	16

The major initiatives we’re delivering this year	16

How we’re measuring progress over four years	17

# Economy of the Future

Over the next four years, we will focus on driving economic recovery and creating the conditions for a strong, adaptive, sustainable and thriving future city economy supported by a diverse mix of industries and jobs that provide dignity and opportunity.

Highlights for quarter three (January to March 2022) Events and activations continued to drive high visitation numbers and activity across the city. The 2022 Moomba Festival was hugely successful with over one million people celebrating in the city over the long weekend. Supporting our city businesses remained a strong focus with $100,000 in funding through the Business Event Sponsorship Program being awarded to support conferences and other forums delivered before June. In partnership with the State Government, the Midweek Melbourne Money program returned to encourage workers and visitors back to the city, with another $10 million program launched on 7 March. The two previous rounds saw more than $61million flow back to the city’s businesses. The Business Concierge Service continued its outreach and support, with 5,600 interactions during the period and a dedicated Business Breakfast was held at Town Hall on 17 March for industry leaders to share insights and discuss the revitalisation of Melbourne’s economy. A range of initiatives to support and welcome international students were also rolled out to coincide with the start of the academic year, including programs at The Couch, International Student Centre. Community consultation also opened this month on the voluntary local review of City of Melbourne’s progress towards the United Nations Sustainable Development Goals. Our progress As a State owned asset, the Central Pier redevelopment is delayed as key milestones and timeframes are driven by Development Victoria and Department of Transport. No significant issues have impacted on our progress towards meeting our target outcomes.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Continue to strengthen Melbourne’s economic recovery, including through precinct and shopfront activation, delivery of an enhanced business concierge service and support for the night-time economy. | Deliver | On track |
| Ensure Melbourne is the easiest place to start and grow a business through the establishment of Invest Melbourne. | Deliver | On track |
| Drive economic growth and resilience by implementing the Economic Development Strategy, focusing support on existing and emerging industry sectors. | Deliver Partner | On track |
| Work in partnership with the Victorian Government and other stakeholders to advocate for and deliver integrated high-quality public and active transport in urban renewal areas. | Partner | Not started |
| Establish a new tourism entity called Visit Melbourne and review and refresh the program of City of Melbourne-owned and sponsored events to maximise opportunities to drive visitation and spend. | Deliver Partner | On track |
| Market and promote Melbourne as a great place to live for all, while ensuring key workers have access to affordable housing. | Deliver | On track |
| Increase visitation to Docklands by partnering with the Victorian Government and key stakeholders to enable reconstruction and redevelopment in Central Pier and surrounds. | Partner Advocate | Delayed |
| Review Melbourne’s international relationships to optimise future and existing partnerships to enable mutual growth and opportunity. | Deliver | On track |
| Partner with industry to support the development of globally competitive innovation ecosystems. | Partner Deliver | On track |
| Develop a corporate strategy for the City of Melbourne to drive exemplary customer service, digitise services and operations, improve productivity and identify new revenue opportunities. | Deliver | On track |
| Embed the Sustainable Development Goals in the way City of Melbourne plans, prioritises its investments, reports and benchmarks against other cities. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Capital city gross local product. | Increase |
| Number of businesses in the municipality. | Increase |
| Number of start-ups in the municipality. | Increase |
| Vacancy rate of retail premises. | Decrease |
| Proportion of residents employed in the municipality. | Increase |
| Gross local product per capita per person employed. | Increase |
| Number of jobs in the municipality. | Increase |
| Number of visitors to the municipality. | Increase |
| Planning applications decided within required timeframes. | 100% |

# Melbourne’s unique identity and place

Over the next four years we will celebrate and protect the places, people and cultures that make Melbourne a unique, vibrant and creative city with world-leading liveability.

Highlights for quarter three (January to March 2022) Australia’s largest free community festival, Moomba, returned to the banks of the Yarra River this quarter along with several signature Melbourne events including the Australian Open, Melbourne Food and Wine Festival, Melbourne Fashion Festival and Round 1 of the AFL Round 1. Tom Nicholson’s new public artwork ‘Chimney in store (Towards a monument to Batman’s Treaty)’ was launched at Batman Park. Work continued on the structure and precinct plans for Macauley, Arden, Fishermen's Bend and the National Employment and Innovation Cluster. Public consultation was undertaken for the Carlton Heritage Review Amendment C405, eight development projects were reviewed by the newly formed Melbourne Design Review Panel, and we led three public design events at MPavilion and contributed to five other design events as part of Melbourne Design Week. The Queen Victoria Market Precinct Renewal Program continued to progress towards the vision of a world-class market with works commencing to create a contemporary new Food Hall and installation of essential services for fruit and vegetable traders. Consultation commenced with Traditional Owners and via Participate Melbourne to inform the detailed designs of the new Munro Library and Community Hub. An Expression of Interest was launched calling for local and international design consultants interested in designing Greenline as part of a 2-stage process. An on-site panel ‘Greenline the Big Picture’ was held in association with Open House Melbourne and the reopening of Enterprize Park saw the completion of one of Greenline's first program milestones. Our progress Queen Victoria Market and Munro Community Hub have faced some delivery pressures, partly from COVID-related impacts. Otherwise, no significant issues have impacted on our progress towards meeting our target outcomes this quarter.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Partner with the Victorian Government and other stakeholders to deliver specific components of Greenline along the north bank of the Yarra River. | Deliver Partner | On track |
| Increase the amount of public open space in the municipality with a focus on areas of greatest need. | Deliver | On track |
| Celebrate, partner and advocate for investment in the city’s three key waterways, the Yarra River-Birrarung, the Maribyrnong and Moonee Ponds Creek. | Partner Advocate | On track |
| Play a lead role in facilitating the delivery of high-quality and climate adapted urban renewal in Arden and Macaulay, Fishermans Bend, and Docklands in partnership with the Victorian Government. | Partner | On track |
| Adopt the Municipal Planning Strategy in 2022-23. | Deliver | On track |
| Complete heritage reviews and implement associated planning scheme amendments to protect and celebrate heritage in our municipality. | Deliver | On track |
| Protect Queen Victoria Market as a traditional open-air market. | Deliver | Delayed |
| Deliver Queen Victoria Market6 precinct improvements. | Deliver Partner | Delayed |
| Deliver public art projects that reflect Melbourne’s unique culture and heritage. | Deliver | On track |
| Facilitate increased investment in unique Melbourne events to further activate and celebrate the city. | Partner | On track |
| Champion high quality development and public realm design through delivering the Design Excellence Program. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of residents within 300m of public open space. | Increase |
| Proportion of people surveyed who visit a park in the municipality on a regular basis. | Increase |
| Area of new public open space in Southbank. | 1.1ha (by 2025) |
| Neighbourhoods in the municipality with up-to-date local heritage studies and controls. | 100% |
| Proportion of people who support the city being made up of different cultures. | 100% |
| Value of the creative sector to the local economy. | Increase |
| The number of creative spaces in the municipality. | Increase |
| The number of artists supported by City of Melbourne through city planning, design and city operations. | Increase |
| The number of design reviews of major projects. | Increase |

# Aboriginal Melbourne

For the Wurundjeri, Bunurong, Taungurung, Dja Dja Wurrung and Wadawurrung peoples of the Eastern Kulin, the place now known as Melbourne has always been an important meeting place and location for events of political, cultural, social and educational significance. Over the next four years, we will ensure that First Peoples’ culture, lore, knowledge, and heritage enrich the city’s growth and development.

Highlights for quarter three (January to March 2022) Planning and organisation have continued on a series of truth telling activities scheduled for Melbourne Knowledge Week, National Reconciliation Week and NAIDOC Week during 2022. Planning and organisation is taking place for truth telling activities in 2023. Preparations are under way for the launch of phase one of the Aboriginal Melbourne Digital Map during Melbourne Knowledge Week. This has been developed with Wurundjeri Woi Wurrung and Bunurong Boon Wurrung Elders. Preparations are underway for National Reconciliation Week which takes place from the 27 May until 3 June. Highlights include an Oration by Adam Briggs and a range of children’s activities across all libraries in the city. The week concludes on Mabo Day with a concert at Federation Square. NAIDOC week activities planning and organisation continues including a pre-school/early primary school education program is being developed in partnership with Wurundjeri Council and Museum Victoria. A pre-feasibility study on the First Nations Cultural Precinct has been submitted to the Victorian Government for funding consideration. Our progress No significant issues have impacted on our progress this quarter towards meeting our target outcomes.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Explore and deliver opportunities for ‘truth-telling’ to facilitate learning, healing, and change within Melbourne and beyond. This will be an opportunity to impart knowledge of thousands of years of rich history, language and stories, as well as provide a form of restorative justice by acknowledging Aboriginal peoples’ experiences of dispossession and inequity. | Partner | On track |
| Implement the Declaration of Recognition and Commitment in good faith which signals and elevates the City of Melbourne’s shared commitment for reconciliation across the whole of the organisation. | Deliver | Completed |
| Govern with Sovereign First Nations to enable true self-determination, where deliberative engagement is proactive, responsive and consistent. | Deliver | On track |
| Commence planning for a co-designed First Nations Cultural Precinct with First Peoples – a place to retain, maintain and recreate in a culturally specific geography, where First Peoples can practice continuity of customs and traditions, through uninterrupted connection to lands and waters. | Partner | On track |
| Support a partnership forum – an annual gathering of the Eastern Kulin (noting the history of Tanderrum). | Partner | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of people surveyed who demonstrate an understanding of Melbourne’s Aboriginal heritage and culture. | 100% |
| Proportion of people surveyed who believe the relationship with Aboriginal people is important. | 100% |
| Delivery of the City of Melbourne’s Reconciliation Action Plan. | 100% |
| Level of involvement of Traditional Custodians in city governance. | Increase |

# Climate and biodiversity emergency

Over the next four years, we will prioritise our environment and take urgent action to reduce emissions and waste in order to protect public health, strengthen the economy and create a city that mitigates and adapts to climate change. The City of Melbourne declared a climate and biodiversity emergency in 2019.

Highlights for quarter three (January to March 2022) The City of Melbourne’s food waste recycling service has been further expanded to include low rise apartments. This service is now utilised by almost 15,000 households, diverting more than 120 tonnes of food organic waste from landfill every month. A trial to recycle soft plastic commenced in partnership with Cleanaway as part of our kerbside recycling service – helping to reduce waste to landfill. Our largest Moomba ever received Climate Active carbon neutral certification. Council has committed to upgrade North Melbourne Town Hall to be gas free and the Kensington Recreation Centre design and construction contract was awarded for all-electric build, as outlined in the Emissions Reduction Plan. Power Melbourne Expressions of Interest for commercial partners closed on 11 February and evaluation of proposals received is currently underway. The annual tree planting program started in March. This is supported by two new monitoring programs for City of Melbourne trees There has been a successful and positive community consultation around planting productive and native plants along the Kensington Stock Route, with lots of community interest surrounding native plants. Round four of the Urban Forest Fund Grants Program has closed and 10 eligible applications have been assessed. Recommendations for funding the successful grants are currently being finalised Our progress Exhibition of Amendment C376 to improve environmental performance of buildings has been delayed. Otherwise, no significant issues have impacted on our progress towards meeting our target outcomes this quarter.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| To enhance Melbourne’s position as a global leader on climate action, we will undertake bold advocacy on behalf of our community. | Deliver | On track |
| Create an enabling environment for Melbourne businesses and universities to become the employment centre of a resilient zero-carbon economy. | Deliver | On track |
| Progress a planning scheme amendment to improve the environmental performance of buildings in order to reduce emissions to zero by 2040. | Deliver Partner | Delayed |
| Deliver on our Urban Forest Strategy including tree canopy, private greening incentives and city greening. | Partner | On track |
| Lead the reduction of food waste and diversion of waste from landfill, by continuing the Food Organics, Green Organics rollout through high-rise apartment innovation and by addressing food-waste reduction. | Deliver Partner | On track |
| Support the development of a circular economy through bold leadership and community neighbourhood projects, including the container deposit scheme, alternative waste technologies, circular economy guidelines and partnered or aggregated demand to stimulate end markets. | Deliver | On track |
| Support the development of battery storage and renewable energy in the municipality through the Power Melbourne initiative. | Partner Advocate | On track |
| Implement the Climate and Biodiversity Emergency action plan. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Municipal greenhouse gas emissions. | 33% reduction (from 2015 baseline by 2025) |
| On-road transport emissions. | Decrease |
| Installed battery storage capacity in the municipality. | Increase |
| Household waste produced. | 10% reduction (by 2025) |
| Municipal waste diverted from landfill. | 50% increase (by 2025) |
| Alternative water use. | Increase |
| Stormwater quality. | Increase |
| Hospital admissions in relation to extreme weather events. | Decrease |
| Percentage of tree canopy cover in the public realm. | 27% (by 2025) |
| Number of trees planted in the municipality. | 2400 plus number of trees removed in previous year, or 3000, whichever is more. |
| Area of native understorey habitat in the public realm. | Increase |

# Access and affordability

Over the next four years, we will reduce economic and social inequality by ensuring universal access to housing, core services and information.

Highlights for quarter three (January to March 2022) Construction of the Western Pavilion building is complete and the old pavilion demolished. Landscaping works are underway. User groups have commenced utilising the new building. The Brens Pavilion project is underway and expected to be completed by early 2023. As part of the Neighbourhood Model we have launched consultations for the remaining eight neighbourhoods and are undertaking the second phase consultations for CBD and Kensington. As part of City of Melbourne's Disability Access and Inclusion Plan (DAIP) and in partnership with Hidden Disabilities and Travellers Aid, volunteers handed out over 259 Sunflower lanyards, pins, and wristbands to Moomba patrons who may have a hidden disability. The sunflower symbol makes it easier to identify patrons that may need additional assistance. Two library pop-ups opened in this quarter: Federation Square focussing on children and families; 185 Lygon Street Carlton focussed on writing. The library van was launched on 28 March. It will visit neighbourhoods to highlight library services and to provide access to free Wi-Fi. Community consultation regarding the new library at the Munro development was completed. Our progress No significant issues have impacted on our progress this quarter towards meeting our target outcomes.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Increase and upgrade accessible, inclusive spaces for women in City of Melbourne sports facilities | Deliver | On track |
| Implement a neighbourhood model by working with communities to develop neighbourhood plans and neighbourhood service centres that respond to the local community’s existing and projected needs. | Deliver | On track |
| Deliver a revitalised library network, including pop-up libraries, to increase access for our diverse community and to help revitalise the city. | Deliver | On track |
| Deliver the Disability Access Plan 2020–2024 including ensuring our services and events are more accessible, increasing the number of accessible adult change facilities, and partnering with community and transport groups to make transport more accessible. | Deliver Partner | On track |
| Develop and deliver initiatives and programs that will provide food relief to vulnerable members of our community and improve local food production by supporting communities to grow their own food. | Deliver Partner Advocate | On track |
| As part of a new corporate strategy for the City of Melbourne, ensure our core services remain accessible and affordable. | Deliver | Not started |
| In partnership with the Victorian Government commence construction on a replacement North Melbourne Community Centre precinct for the Melrose St community and growing Macaulay population. | Deliver Partner | On track |
| Deliver programs that will build digital literacy skills and capabilities, improve access to free Wi-Fi from our community facilities and advocate for appropriate digital infrastructure, to improve digital inclusion for all, particularly for vulnerable groups. | Deliver | On track |
| Create a new entity ‘Homes Melbourne’, to coordinate and facilitate more affordable housing for key workers and people on low-incomes and progress a demonstration project on Council-owned land, support the Make Room accommodation project and new homeless support hubs for vulnerable citizens to access essential support. | Partner | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Number of people sleeping rough who have not been offered accommodation. | Zero |
| Number of people supported through a range of accommodation including long-term supportive housing and affordable housing. | 500 (by 2025) |
| Number of new demonstration social and affordable housing units facilitated on City of Melbourne land. | 100 (by 2025) |
| Proportion of people reporting food insecurity. | 25% reduction (by 2025) |
| Proportion of people surveyed who participate in lifelong learning in the municipality. | Increase |
| Proportion of people surveyed who participate in arts and cultural activities in the municipality. | Increase |

# Safety and wellbeing

Over the next four years, we will plan and design for the safety and wellbeing of those who live, visit, work and do business in Melbourne, regardless of their background.

Highlights for quarter three (January to March 2022) The e-scooter trial, in partnership with the Victorian Government started this quarter on 1 February and continues for the next 12 months. So far, more than 500,000 trips have been taken, with 60 per cent of all trips within the City of Melbourne. More than 170 new jobs have been created. Officers are continuing to collaborate with stakeholders to address footpath riding, carrying passengers, underage riding and riding without helmets. Data for March shows bike and scooter volumes on protected routes surrounding the central city has jumped 42 per cent month on month. Construction of new bike lanes on Princes Park Drive and College Crescent are complete. These upgraded routes are being used increasingly by riders. Works to the dog park and skate space in the southern City Road undercroft are complete and open for use. The Inclusive Melbourne Strategy was adopted by the Future Melbourne Committee on 15 February 2022. It outlines how the City of Melbourne will embrace the diversity of cultures, ages, genders, sexualities, backgrounds, religions and abilities of the people who live, work, study and visit the city. Our progress Some elements of the bike lane program and work on station precincts have had to be deferred, and there are minor delays associated with works around the Transport Amenity Program and City Road northern undercroft. Otherwise no significant issues have impacted on our progress towards meeting our target outcomes this quarter.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Continue to implement the Transport Strategy 2030, including delivery of a protected bike lane network, station precincts, streets for people, safer speed limits, etcetera. | Advocate Partner Deliver | Delayed |
| Deliver the North and West Melbourne and Docklands Transport and Amenity Program in partnership with the Victorian Government. | Deliver Partner | Delayed |
| City of Melbourne will design and deliver the upgrades to the City Road northern undercroft by end of 2023-2024 and advocate for the full delivery of upgrades to the City Road East and West. | Deliver Advocate | Delayed |
| Adopt in 2021-22 and then implement an Inclusive Melbourne Strategy that will increase access to opportunities for all people who live, work, study in and visit the city. | Deliver | On track |
| We will be a leading organisation on equality and inclusion and deliver programs in communities that will reduce physical and psychological harm to all people. | Deliver | On track |
| We will continue to work with Victoria Police and other agencies to deliver a range of initiatives that improve safety on the streets of Melbourne and within our communities. | Partner Deliver | On track |
| Deliver and maintain a clean city through the Rapid Response Clean Team initiative. | Deliver | On track |
| Engage and prepare residents and communities to enhance their resilience to hazards, disasters and the health impacts of climate change. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of people who report feeling safe in the city. | 90% by day, 65% by night |
| Melburnians’ self-reported sense of belonging to community. | At least 70 /100 |
| Rate of recorded family violence incidents. | Decrease |
| Complaints of discrimination based on sexual orientation, sexuality, disability, sex, gender, race, religious or political beliefs or other grounds for unlawful discrimination. | Decrease |
| Proportion of adults who get adequate physical exercise. | Increase |
| Rate of ambulance attendance for alcohol and drug misuse in the municipality. | Decrease |
| Number of transport related injuries and fatalities. | Decrease |
| Proportion of trips made by public transport, bicycle or on foot. | Increase |

# Footnotes

https://www.melbourne.vic.gov.au/business/Pages/business-concierge-service.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/Pages/economic-development-strategy-2031.aspx

https://www.melbourne.vic.gov.au/arts-and-culture/strategies-support/funding/Pages/event-partnership-program.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/Pages/united-nations-sustainable-development-goals.aspx

https://participate.melbourne.vic.gov.au/greenline/implementation-plan-overview

https://participate.melbourne.vic.gov.au/city-river-strategy

https://participate.melbourne.vic.gov.au/arden/plan

https://participate.melbourne.vic.gov.au/macaulay-refresh

https://www.fishermansbend.vic.gov.au

https://www.melbourne.vic.gov.au/qvmrenewal

https://participate.melbourne.vic.gov.au/design-excellence-program

https://www.melbourne.vic.gov.au/community/greening-the-city/urban-forest/pages/urban-forest-strategy.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/eco-city/climate-change/Pages/taking-action-climate-change.aspx?k=climate+and+biodiversity+emergency&type=web

https://participate.melbourne.vic.gov.au/disability-access-plan

https://www.melbourne.vic.gov.au/parking-and-transport/transport-planning-projects/Pages/transport-strategy.aspx

https://participate.melbourne.vic.gov.au/inclusive-melbourne-strategy