# Elizabeth Street South Streetscape Improvements

## Construction update

### May 2021

### The Elizabeth Street streetscape works are progressing well with a considerable amount of work carried out since works commenced in February.

### Works update

### Demolition of the roadway and part of the footpath has been completed, along with installation of in-ground infrastructure services such as electrical cables and stormwater drainage.

### Signals, drainage and paving works at the Elizabeth Street and Flinders Lane intersection are continuing and will be completed by the end of May.

### Paving of the new pedestrianised area has also commenced and will continue over the next six weeks.

### Towards the end of April, the 120-year-old brick drain beneath Elizabeth Street was exposed in order for Melbourne Water to inspect the condition of the drain.

### Works to expand the footpath and upgrade signals will commence at the Elizabeth Street and Flinders Street intersection at the end of May.

### Updated timeframe

### In line with Melbourne Water requirements, a new protective slab needs to be installed over the brick drain to prolong the life of the drain. This work was not part of the original scope of the project.

### The slab works will take approximately four week to complete, resulting in the completion date for the project shifting to the end of June instead of the end of May.

### We apologise for this unavoidable delay in the program.

First pavers for the new pedestrianised area being laid

d

Exposed 120-year-old brick drain

To find out more, please contact 9658 9658, or visit melbourne.vic.gov.au/cityprojects or melbourne.vic.gov.au/contactus

# Footnotes

https://www.melbourne.vic.gov.au/building-and-development/shaping-the-city/city-projects/Pages/city-projects.aspx

https://www.melbourne.vic.gov.au/Pages/contact-us.aspx